## DOP
Global Sprint 34 - DOP
The DOP contains all the plans for in the Deployment of SPDRs NA and SSGAFunds project. If there is any concern please contact the developer,contacts information can be found in the Contact Detail Sheet
PRE UAT DEPLOYMENT
Deployment Time |  | Activity | Owner | Status
China | US
NA | 2017-07-24 | PREPARE DM/DC and DOP | Puru | Completed
UAT DEPLOYMENT (if any show stoppers during China time, Boston Resource will pick up Deployment during EST)
Deployment Time |  | Activity | Owner | Status
China (CST) | US(EST)
2017-07-25 09:00 | NA | Submit DCs | Star | completed
2017-07-25 09:00 | NA | Staging DCs | Star | completed
2017-07-25 09:00 | NA | Proxy Approve | Devarshi/Gil | completed
2017-07-25 09:00 | NA | Deploy DCs | DS TEAM | completed
2017-07-25 09:00 | NA | Teamsite Refresh From PROD to UAT | Chris | Pending
2017-07-25 09:00 | NA | Developer Check Out | Surendar/Alison/Liam | Pending
Post UAT DEPLOYMENT
Deployment Time |  | Activity | Owner | Status
China (CST) | US(EST)
NA | 2017-07-25 09:00 | UAT Testing | Surendar/Alison/Liam | Pending
Production Code merge would be done by Puru and Prashanth would do NEWDEVX deployment for SPDRs NA, EMEA and do smoke test before FINAL UAT Deployment
Final UAT DEPLOYMENT (if any show stoppers during China time, Boston Resource will pick up Deployment during EST)
Deployment Time |  | Activity | Owner | Status
China (CST) | US(EST)
2017-07-27 09:00 | NA | Submit DCs | Star/Puru | Pending
2017-07-27 09:00 | NA | Staging DCs | Star/Puru | Pending
2017-07-27 09:00 | NA | Proxy Approve | Gil/Devarshi | Pending
2017-07-27 09:00 | NA | Deploy DCs | DS TEAM | Pending
2017-07-27 09:00 | NA | Teamsite Refresh From PROD to UAT | Chris | Pending
2017-07-27 09:00 | NA | Developer Check Out | Surendar\Alison\Liam | Pending
The procedure is added to the DOP for the quality and stalibily purpose.Please provide the sign off, so the developer can merge the code to production branch.
PROD DEPLOYMENT
Deployment Time |  | Activity | Owner | Status
China (CST) | US(EST)
Jul 28 1:00 PM - Jul 28 2:00 PM | NA | Submit DM and DCs | Star | Pending
2017-07-28 13:00 | NA | Send Email to Support Team | Star | Pending
2017-07-28 14:00 | NA | JOBS ON HOLD | Star | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260033 (IBGTools DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260006 (EMEA DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260000 (SPDRs DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260012 (SSGAFunds DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260021(Autosys Jobs DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Deploy DC# SSgAP01260056(Endeca Search DC) | DS TEAM | Pending
Jul 28 2:00 PM - Jul 28 4:00 PM | NA | Teamsite file updates | Chris/Wenwen | Pending
2017-07-28 14:30 | NA | Proxy Approve | Gil/Devarshi | Pending
Jul 28 4:00 PM - Jul 28 4:45 PM | NA | Rollback if needed, See Rollback Strategy | DS TEAM | Pending
Jul 28 4:00 PM - Jul 28 4:15 PM | NA | JOB OFF HOLD | Star | Pending
Jul 28 4:15 PM - Jul 28 4:30 PM | NA | Execute Update Version and Developer Checkout | Star | Pending
2017-07-28 17:00 | NA | Inform All Stakeholders | Star/Gil/Ruchi | Pending
NA | Jul 28 8:45 AM -Jul 28 9:00 AM | PROD Deplyment Status check | Ruchi | Pending
Jul 28 5:00 PM -Jul 28 8:30 PM | Jul 28 9:00 AM -Jul 28 11:00 AM | PROD CHECK OUT | BUSINESS | Pending
Deploy DCs: Make sure deploy before 7:00 PM EST Time. Note will be put on the comment of the DC. When All Deployments are completed. ALL sites related AutoSys job will be off hold immediately.

## Contact Detail
Contact Detail
Name | ID | Email | Phone
Purusotham Annamalai | t619064 | purusotham_annamalai@ssga.com | 617-893-7558
Prashanth Vootla | t606757 | prashanth.vootla@ssga.com | 312-618-3339
Mounir Abboud | p613634 | Abboud, Mounir <Mounir_Abboud@ssga.com>
Chen Xing (Star) | e619543 | Chen, Xing (Star) <Xing_Chen@ssga.com>
Tianbo | e619543 | Ruan, Tianbo <Tianbo_Ruan@ssga.com>
Andrew Schneider | e513854 | Schneider, Andrew <Andrew_Schneider@ssga.com> | 617-905-4762
Ruchi Dwivedi | t612520 | Dwivedi, Ruchi <Ruchi_Dwivedi@ssga.com> | 978-729-0300
Evers Alison |  | alison_evers@ssga.com | 508-308-5120
Michelle Cugini |  | Cugini, Michelle | 617-378-8409
Zhao, Yue (Yves) |  | Yue_Zhao@SSgA.com
SurendarMadadi, Surendar |  | Madadi, Surendar <Surendar_Madadi@Ssga.com> | 732-208-1827
Liya Peng |  | Peng, Liya <Liya_Peng@ssga.com>
Chris Chaloner |  | Chaloner, Christian <Christian_Chaloner@ssga.com>
Wenwen Zheng |  | Zheng, Wenwen <Wenwen_Zheng@SSgA.com>
Cherish |  | Chen, Qi (Cherish) <Qi_Chen@ssga.com>

## DM&DC
DM/DC Detail
DM:SSgAP01252731
DC NUMBER | APPLICATION NAME | PLATFORM | Note
1. SSgAP01260033 | IBG Tools | World wide Web
2. SSgAP01260000 | SPDRs NA | World wide web
3. SSgAP01260006 | EMEA | World wide web
4. SSgAP01260012 | SSgaFunds | World wide web
5.SSgAP01260021 | Autosys Jobs | Austosys
6.SSgAP01260056 | Endeca search

## Static File List
Static File List
SPDRS
//gaintuat01/default/main/SPDRs.com/STAGING/content/site-content2g/css/spdr_new.css
//gaintuat01/default/main/SPDRs.com/STAGING/content/site-content2g/html/footer_new.html
//gaintuat01/default/main/SPDRs.com/STAGING/content/site-content2g/scripts/spdr_new.js
EMEA
//gaintuat01/default/main/spdrseurope/STAGING/site-content2g/scripts/spdr.js
SSGAFUNDS
Update Version
SPDRS
https://gvwlsprd57.ssga.statestr.com:60810/seam/resource/updateVersion https://gvwlsprd58.ssga.statestr.com:60810/seam/resource/updateVersion
EMEA
https://gvwlsprd57.ssga.statestr.com:60816/seam/resource/updateVersion https://gvwlsprd58.ssga.statestr.com:60816/seam/resource/updateVersion
SSGAFUNDS
https://gvwlsprd57.ssga.statestr.com:60812/seam/resource/updateVersion https://gvwlsprd58.ssga.statestr.com:60812/seam/resource/updateVersion

## Autosys Job
AutoSys Job on Hold
ssgai_ibg_new_opendeploy
ssgai_emea_opendeploy
Send Email
JOBOnHold / JobOffHold command
/usr/local/bin/pbrun -u tsapp /tools/autosys/bin/sendevent -j ssgai_ibg_new_opendeploy -E JOB_ON_HOLD
/usr/local/bin/pbrun -u tsapp /tools/autosys/bin/sendevent -j ssgai_emea_opendeploy -E JOB_ON_HOLD
/usr/local/bin/pbrun -u tsapp /tools/autosys/bin/sendevent -j ssgai_ibg_new_opendeploy -E JOB_OFF_HOLD
/usr/local/bin/pbrun -u tsapp /tools/autosys/bin/sendevent -j ssgai_emea_opendeploy -E JOB_OFF_HOLD

## Run SQL
BAS RUN SQL:

## InfrastructureChanges
URL Redirection for Strategy Pages

## DEPLOYMENT ROLL BACK STATEGE
Rollback Strategies for Deployment
DC Number | Rollback Strategies | PLATFORM
SSgAP01260033 | 1) previous ear file is back up before deployment | WEB
SSgAP01260000 | 2) restore previous ear file from back up file
SSgAP01260006 | 3) recycle weblogic servers
SSgAP01260012
SSgAP01260021
SSgAP01260056